Here is a comprehensive Integration Suite Migration Project Runbook Framework covering all the sections you requested:

Integration Suite Migration Project Runbook

Framework & Execution Guide

Version: 1.0
Scope: 100+ Integrations | Generic Migration Framework
Audience: Technical Leads, Integration Architects, Project Managers, Basis/Ops Teams

Table of Contents

1. Project Overview & Assumptions

2. Important Questions to Ask Before Migration

3. System Readiness Checklist

4. RACI Matrix

5. Naming Convention Guide

6. Integration Pattern Selection Process

7. Pre-Migration Assessment

8. Configuration Guide
8a. S/4HANA Inbound & Outbound
8b. Cloud Connector
8c. BTP Cockpit
8d. Integration Suite (IS)

9. 8a. S/4HANA Inbound & Outbound

10. 8b. Cloud Connector

11. 8c. BTP Cockpit

12. 8d. Integration Suite (IS)

13. Migration Execution Steps

14. Testing & Validation

15. Cutover & Rollover Considerations

16. Rollback Procedures

17. Go-Live Checklist

18. Things That Can Go Wrong (Risk Register)

1. Project Overview & Assumptions

1.1 Project Context

| Field | Details |
| --- | --- |
| Project Name | Integration Suite Migration |
| Migration Type | Legacy/Source Platform → Target Integration Suite |
| Total Integrations | 100+ |
| Environments | DEV / QA / UAT / PROD |
| Migration Approach | Phased / Wave-based |
| Target Platform | SAP Integration Suite (or equivalent) |

1.2 Assumptions

• All source integration artifacts have been inventoried and documented prior to migration start.

• Business owners are identified for each integration and are available for UAT sign-off.

• Source system credentials, certificates, and connection details are available and accessible.

• Downtime windows have been agreed upon with business stakeholders for each wave.

• The target Integration Suite environment is provisioned, licensed, and accessible before migration begins.

• Naming conventions defined in this runbook will be adopted for all new artifacts — no exceptions.

• All integrations will be re-tested end-to-end in the target environment regardless of complexity.

• Rollback to the source platform is possible within the agreed cutover window.

• Security reviews and access provisioning will not block migration timelines if initiated early.

• Third-party systems (non-SAP) may require separate API key/credential regeneration.

• Cloud Connector is installed, configured, and connected to the BTP subaccount before any on-premise integration is migrated.

• Any custom adapters or non-standard connectors in the source platform must be flagged during assessment.

1.3 Things to Consider (General)

• Not all integrations are equal — prioritize by business criticality, not volume.

• Legacy integrations may have undocumented business logic embedded in mappings — allow time for discovery.

• Certificate expiry dates must be tracked across all environments.

• Some integrations may be candidates for decommission rather than migration — validate with business.

• Error handling and alerting behavior may differ between source and target platforms — re-configure explicitly.

• Timezone handling, date format differences, and character encoding issues are common migration pitfalls.

• Performance benchmarks from the source system should be documented and used as acceptance criteria.

2. Important Questions to Ask Before Migration

2.1 Business & Stakeholder Questions

• Who are the business owners for each integration?

• What is the business criticality (High / Medium / Low) of each integration?

• What is the acceptable downtime window per integration?

• Are there any regulatory or compliance requirements tied to specific integrations?

• Are there any integrations that are scheduled for decommission within 12 months?

• Who has authority to approve go-live for each integration or wave?

• Are there any blackout periods (month-end close, fiscal year-end) that restrict migration windows?

2.2 Technical Discovery Questions

• What is the complete inventory of current integrations (name, type, direction, frequency)?

• What protocols are in use? (REST, SOAP, SFTP, IDOC, RFC, JDBC, etc.)

• Are there any custom adapters or non-standard connectors?

• What authentication mechanisms are in use? (Basic Auth, OAuth 2.0, Certificates, API Keys)

• What are the current SLAs for message processing (latency, throughput)?

• Are there any integrations with large payload sizes (> 40MB)?

• Are there stateful integrations or those relying on persistence/queuing?

• What monitoring and alerting is currently in place?

• Are there any hardcoded values (IP addresses, URLs, credentials) in existing flows?

• What is the current error handling and retry strategy?

2.3 Infrastructure & Environment Questions

• Is the BTP subaccount provisioned and sized correctly for 100+ integrations?

• Is Cloud Connector installed on-premise and connected to BTP?

• Are all required entitlements activated in BTP Cockpit?

• Are firewall rules and network routing updated to allow BTP traffic?

• Are SSL certificates procured and ready for all environments?

• Is there a dedicated Integration Suite tenant for DEV, QA, and PROD?

• Are service accounts and technical users created in all connected systems?

2.4 Governance & Process Questions

• Is there a change management process in place for migrated integrations?

• How will versioning of integration artifacts be managed post-migration?

• What is the incident escalation path during and after migration?

• Is there a knowledge transfer plan for the operations team?

• How will monitoring be handed over from the source platform to the target?

3. System Readiness Checklist

Complete this checklist before starting any migration wave. All items must be confirmed as READY.

3.1 BTP & Integration Suite Readiness

• BTP Global Account and Subaccount created and accessible

• Integration Suite subscription activated and provisioned

• Required capabilities enabled: Cloud Integration, API Management, Event Mesh (if applicable)

• Role collections assigned to all team members (IntegrationDeveloper, IntegrationOperator, etc.)

• Integration Suite DEV / QA / PROD tenants are separate and isolated

• Tenant URLs documented and shared with the team

• Message monitoring is accessible and functional

• Alert rules configured for failed messages

• Keystore populated with required certificates

• Credential store (Security Material) configured with all required credentials

• User-defined variables and externalized parameters are configured

3.2 Cloud Connector Readiness

• Cloud Connector installed on the on-premise host (version aligned with BTP)

• Cloud Connector connected to the correct BTP subaccount

• System mappings configured for all on-premise backend systems (S/4HANA, etc.)

• Resources (paths/RFC function modules) exposed via Cloud Connector

• Connectivity test from BTP to on-premise systems is successful

• High Availability (HA) setup for Cloud Connector confirmed (shadow instance)

• Cloud Connector logs are accessible and monitored

3.3 S/4HANA Readiness

• RFC destinations configured in SM59

• HTTP destinations configured in SM59

• IDocs ports and partner profiles configured (WE20, WE21)

• Outbound message configuration validated (BD64, WE20)

• Technical user created with appropriate authorizations

• Basis team has confirmed system is ready for integration testing

• ALE/EDI configuration reviewed and documented

3.4 Source Platform Readiness

• Full artifact export/backup completed from source platform

• All integration flows documented with current configurations

• Dependency mapping completed (which flows call which)

• All credentials and certificates documented in a secure vault

• Source platform is in a stable state (no pending deployments or incidents)

4. RACI Matrix

| Activity | Integration Architect | Integration Developer | Basis / Ops | Project Manager | Business Owner | Security Team |
| --- | --- | --- | --- | --- | --- | --- |
| Integration Inventory & Assessment | A/R | C | C | I | C | I |
| Naming Convention Definition | A/R | C | I | I | I | I |
| BTP Subaccount Setup | A | R | R | I | I | C |
| Cloud Connector Setup | C | I | A/R | I | I | C |
| S/4HANA Config (SM59, WE20) | C | I | A/R | I | I | I |
| Integration Flow Development/Migration | A/R | R | I | I | I | I |
| Security Material & Keystore Config | A | R | C | I | I | R |
| Unit Testing | C | A/R | I | I | I | I |
| Integration Testing | A/R | R | C | I | C | I |
| UAT Sign-off | C | C | I | A | R | I |
| Cutover Planning | A/R | C | C | R | I | I |
| Go-Live Execution | A/R | R | R | A | I | I |
| Hypercare & Monitoring | C | R | A/R | A | I | I |
| Rollback Execution | A/R | R | R | A | I | I |

Legend: R = Responsible | A = Accountable | C = Consulted | I = Informed

5. Naming Convention Guide

Consistent naming is critical for manageability at 100+ integrations. Enforce from Day 1.

5.1 General Principles

• Use PascalCase or snake_case consistently — pick one and enforce it.

• Never use spaces, special characters, or ambiguous abbreviations.

• Names must be self-describing — a new team member should understand the purpose from the name alone.

• Include environment indicators only in configuration, not in artifact names.

5.2 Integration Flow Naming

Pattern:

{SourceSystem}_{TargetSystem}_{BusinessObject}_{Direction}_{Version}

Examples:

| Flow Name | Description |
| --- | --- |
| S4_SF_Employee_Replication_v1 | S/4HANA to SuccessFactors Employee Replication |
| EXT_S4_PurchaseOrder_Inbound_v2 | External system to S/4HANA Purchase Order Inbound |
| S4_EXT_Invoice_Outbound_v1 | S/4HANA to External system Invoice Outbound |
| BTP_EXT_Notification_Async_v1 | BTP to External Notification (Async) |

5.3 Package Naming

Pattern:

{Domain}_{SourceSystem}_{TargetSystem}_{Description}

Examples:

Finance_S4_EXT_InvoiceProcessing
HR_SF_S4_EmployeeSync
Procurement_EXT_S4_PurchaseOrders

5.4 Security Material (Credentials) Naming

Pattern:

{System}_{Environment}_{AuthType}_{Purpose}

Examples:

S4_PROD_BasicAuth_RFC
SF_QA_OAuth_API
SFTP_PROD_SSHKey_FileTransfer

5.5 Value Mapping Naming

Pattern:

VM_{SourceSystem}_{TargetSystem}_{ObjectType}

Examples:

VM_S4_SF_CostCenter
VM_EXT_S4_CountryCode

5.6 Message Mapping Naming

Pattern:

MM_{SourceFormat}_{TargetFormat}_{BusinessObject}

Examples:

MM_IDoc_JSON_SalesOrder
MM_XML_REST_Employee

5.7 Environment Variables / Externalized Parameters

Pattern:

{System}_{Parameter}_{Environment}

Examples:

S4_ReceiverURL_PROD
SF_APIEndpoint_QA
SFTP_Host_DEV

6. Integration Pattern Selection Process

Use this decision framework to select the right integration pattern for each flow.

6.1 Pattern Decision Tree

Is the integration real-time or batch?
│
├── Real-Time
│   ├── Is a response required? (Synchronous)
│   │   ├── YES → Request-Reply Pattern (Sync)
│   │   └── NO  → Fire-and-Forget / Async Pattern
│   │
│   └── Is there fan-out to multiple receivers?
│       ├── YES → Recipient List / Multicast Pattern
│       └── NO  → Point-to-Point Pattern
│
└── Batch
    ├── File-based? → File Transfer / Polling Pattern
    ├── Database-based? → JDBC Polling Pattern
    └── IDoc/ALE-based? → IDoc Bulk Processing Pattern

6.2 Pattern Reference Table

| Pattern | Use Case | Adapter | Notes |
| --- | --- | --- | --- |
| Point-to-Point (Sync) | Real-time API call with response | HTTP / SOAP / RFC | Keep payload small; set timeouts |
| Point-to-Point (Async) | Fire-and-forget notifications | HTTP / IDoc | Use JMS queue for reliability |
| Content-Based Routing | Route messages based on content | Any | Use Router step; document routing rules |
| Recipient List | Broadcast to multiple systems | Any | Define all receivers explicitly |
| Aggregator | Combine multiple messages | Any | Define correlation ID and completion condition |
| File Transfer | Batch file exchange | SFTP / FTP | Define polling schedule; handle duplicates |
| IDoc Processing | SAP-to-SAP or SAP-to-EXT | IDoc | Validate partner profiles in WE20 |
| Event-Driven | Trigger on business event | AMQP / Kafka / Event Mesh | Define event schema upfront |
| API Proxy | Expose internal APIs externally | API Management | Apply policies: throttling, auth, logging |
| Polling / Scheduled | Periodic data sync | JDBC / OData / SFTP | Define schedule; handle delta logic |

6.3 Pattern Selection Criteria

When selecting a pattern, answer these questions:

1. Timing: Real-time, near-real-time, or batch?

2. Direction: Inbound, outbound, or bidirectional?

3. Volume: Message size and frequency?

4. Reliability: Is guaranteed delivery required?

5. Error Handling: What happens on failure? Retry? Dead-letter queue?

6. Security: What authentication and encryption is required?

7. Transformation: Is data mapping required? Simple or complex?

7. Pre-Migration Assessment

7.1 Integration Inventory Template

For each integration, capture:

| Field | Description |
| --- | --- |
| Integration ID | Unique identifier (e.g., INT-001) |
| Integration Name | Descriptive name |
| Source System | System sending the message |
| Target System | System receiving the message |
| Direction | Inbound / Outbound / Bidirectional |
| Protocol | REST / SOAP / SFTP / IDoc / RFC / JDBC |
| Authentication | Basic / OAuth / Certificate / API Key |
| Frequency | Real-time / Scheduled (cron) / Event-driven |
| Payload Size | Estimated average and peak |
| Business Criticality | High / Medium / Low |
| Business Owner | Name and contact |
| Current Status | Active / Inactive / To Be Decommissioned |
| Migration Wave | Wave 1 / Wave 2 / Wave 3 |
| Dependencies | List of dependent integrations |
| Known Issues | Any known bugs or limitations |
| Migration Complexity | Simple / Medium / Complex |

7.2 Complexity Classification

| Complexity | Criteria |
| --- | --- |
| Simple | Single source/target, no transformation, standard adapter |
| Medium | Basic transformation, 1-2 dependencies, standard protocol |
| Complex | Multi-step routing, custom mapping, large payload, dependencies, non-standard adapter |

7.3 Wave Planning Recommendation

| Wave | Criteria | Target % |
| --- | --- | --- |
| Wave 1 | Low complexity, non-critical, good for learning | ~20% |
| Wave 2 | Medium complexity, moderate criticality | ~50% |
| Wave 3 | High complexity, business-critical, requires extended testing | ~30% |

8. Configuration Guide

8a. S/4HANA — Inbound & Outbound Configuration

Outbound (S/4HANA sending messages)

IDoc Outbound:

• Transaction WE21 — Define port (type: XML HTTP or tRFC)

• Transaction WE20 — Define partner profile (partner type LS)
Message type, IDoc type, receiver port, output mode

• Message type, IDoc type, receiver port, output mode

• Transaction BD64 — Distribution model (for ALE)

• Transaction SM59 — RFC destination to target system or middleware

HTTP/REST Outbound:

• Transaction SM59 — Create HTTP connection
Connection type: G (HTTP connection to external server)
Target host, port, path prefix
SSL client certificate if required

• Connection type: G (HTTP connection to external server)

• Target host, port, path prefix

• SSL client certificate if required

• Activate SSL in SM59 if HTTPS

Inbound (S/4HANA receiving messages)

IDoc Inbound:

• Transaction WE20 — Define inbound partner profile
Message type, process code

• Message type, process code

• Transaction WE57 — Assign function module to message type (if custom)

• Transaction BD51 — Check inbound function module settings

HTTP/SOAP Inbound:

• Transaction SICF — Activate required ICF services

• Transaction SU01 — Create technical user with appropriate roles

• Whitelist Integration Suite IP ranges in network/firewall

Key S/4HANA Transactions Reference

| Transaction | Purpose |
| --- | --- |
| SM59 | RFC/HTTP Destinations |
| WE20 | Partner Profiles (IDoc) |
| WE21 | IDoc Ports |
| BD64 | Distribution Model |
| SICF | ICF Service Activation |
| SU01 | User Management |
| SM58 | tRFC Monitor |
| BD87 | IDoc Status Monitor |
| WE05 | IDoc List |
| SXMB_MONI | XI/PI Message Monitor (if applicable) |

8b. Cloud Connector Configuration

Installation & Initial Setup

1. Download Cloud Connector from SAP Tools portal

2. Install on on-premise host (Java-based, runs as service)

3. Access admin UI: https://localhost:8443

4. Initial login: Administrator / manage

5. Change default password immediately

Connecting to BTP Subaccount

1. Navigate to Connector > Add Subaccount

2. Enter:
Region (e.g., cf.eu10.hana.ondemand.com)
Subaccount ID (from BTP Cockpit)
Subaccount User / Password (P-user or S-user)

3. Region (e.g., cf.eu10.hana.ondemand.com)

4. Subaccount ID (from BTP Cockpit)

5. Subaccount User / Password (P-user or S-user)

6. Verify status shows Connected

Configuring System Mappings (On-Premise Access)

1. Go to Cloud To On-Premise > Access Control

2. Add backend system:
Backend Type: ABAP System / Other
Protocol: HTTP / RFC / LDAP
Internal Host: <hostname> (actual internal hostname)
Internal Port: <port>
Virtual Host: <virtual-hostname> (what BTP sees)
Virtual Port: <virtual-port>

3. Backend Type: ABAP System / Other

4. Protocol: HTTP / RFC / LDAP

5. Internal Host: <hostname> (actual internal hostname)

6. Internal Port: <port>

7. Virtual Host: <virtual-hostname> (what BTP sees)

8. Virtual Port: <virtual-port>

9. Add Resources (paths or RFC function modules to expose)

10. Test connectivity from BTP

High Availability Setup

• Install a Shadow Cloud Connector instance on a separate host

• Connect shadow to the same BTP subaccount

• Shadow takes over automatically if master fails

• Validate HA configuration before go-live

Key Cloud Connector Checks

• Version compatibility with BTP and S/4HANA

• All required backend systems mapped

• All required resources/paths exposed

• SSL certificates configured

• HA shadow instance connected

• Audit logging enabled

8c. BTP Cockpit Configuration

Subaccount Setup

1. Global Account > Create Subaccount
Name: {Project}-{Environment} (e.g., IntMigration-PROD)
Region: Select based on data residency requirements
Subdomain: lowercase, no spaces

2. Name: {Project}-{Environment} (e.g., IntMigration-PROD)

3. Region: Select based on data residency requirements

4. Subdomain: lowercase, no spaces

5. Enable Cloud Foundry environment if required

6. Assign Entitlements:
Integration Suite
Cloud Connector (if applicable)
Event Mesh (if applicable)
API Management

7. Integration Suite

8. Cloud Connector (if applicable)

9. Event Mesh (if applicable)

10. API Management

Role Assignment

| Role Collection | Assign To |
| --- | --- |
| IntegrationDeveloper | Integration developers |
| IntegrationOperator | Ops/monitoring team |
| IntegrationBusinessExpert | Business analysts |
| APIPortal.Administrator | API Management admins |
| Subaccount Administrator | Project leads |

Destinations Configuration

1. Navigate to Connectivity > Destinations

2. Create destination for each target system:
Name: Follow naming convention (Section 5)
Type: HTTP / RFC / Mail
URL: Target system URL
Authentication: Basic / OAuth2 / Client Certificate
Proxy Type: OnPremise (for Cloud Connector) or Internet

3. Name: Follow naming convention (Section 5)

4. Type: HTTP / RFC / Mail

5. URL: Target system URL

6. Authentication: Basic / OAuth2 / Client Certificate

7. Proxy Type: OnPremise (for Cloud Connector) or Internet

8. Test each destination before use in integration flows

Key BTP Cockpit Checks

• Subaccounts created per environment (DEV/QA/PROD)

• Entitlements assigned and quotas sufficient

• All destinations configured and tested

• Role collections assigned to all users

• Trust configuration set up (if using custom IdP)

• Cloud Connector connected and showing green

8d. Integration Suite (IS) Configuration

Initial Setup

1. Subscribe to Integration Suite from BTP Cockpit

2. Launch Integration Suite home page

3. Activate capabilities:
Cloud Integration (mandatory)
API Management (if applicable)
Integration Advisor (for B2B)
Event Mesh (if event-driven)

4. Cloud Integration (mandatory)

5. API Management (if applicable)

6. Integration Advisor (for B2B)

7. Event Mesh (if event-driven)

Security Material Setup

1. Navigate to Monitor > Manage Security > Security Material

2. Add credentials:
User Credentials: Username/password pairs
OAuth2 Client Credentials: Client ID/Secret + Token URL
Keystore: Upload SSL certificates (.p12 / .jks)
Known Hosts: SSH public keys for SFTP
PGP Keys: For encrypted file transfers

3. User Credentials: Username/password pairs

4. OAuth2 Client Credentials: Client ID/Secret + Token URL

5. Keystore: Upload SSL certificates (.p12 / .jks)

6. Known Hosts: SSH public keys for SFTP

7. PGP Keys: For encrypted file transfers

Externalized Parameters (Best Practice)

• Use Externalized Parameters for all environment-specific values

• Never hardcode URLs, hostnames, or credentials in integration flows

• Document all externalized parameters per flow

Integration Flow Deployment Checklist

• Flow configured with externalized parameters

• Security material referenced (not hardcoded)

• Error handling configured (dead-letter, retry, alerts)

• Logging level set appropriately (Info for PROD, Debug for DEV)

• Message processing log (MPL) retention configured

• Flow tested in DEV before promoting to QA/PROD

9. Migration Execution Steps

9.1 Migration Workflow (Per Integration)

Step 1: Assess & Document
   └── Review source flow, document logic, identify dependencies
Step 2: Design in Target
   └── Select pattern, define naming, plan configuration
Step 3: Build / Recreate
   └── Develop integration flow in IS (DEV tenant)
Step 4: Configure Security & Connections
   └── Set up credentials, destinations, Cloud Connector mappings
Step 5: Unit Test (DEV)
   └── Test with sample payloads, validate mappings
Step 6: Promote to QA
   └── Deploy to QA tenant, configure QA-specific parameters
Step 7: Integration Test (QA)
   └── End-to-end test with connected systems
Step 8: UAT
   └── Business owner validates against acceptance criteria
Step 9: Promote to PROD
   └── Deploy to PROD tenant, configure PROD parameters
Step 10: Cutover
    └── Switch traffic from source to target, decommission source flow
Step 11: Hypercare
    └── Monitor for 5–10 business days post go-live

9.2 Wave Execution Plan

| Wave | Integrations | Duration | Go/No-Go Gate |
| --- | --- | --- | --- |
| Wave 1 | ~20 (Low complexity) | 4–6 weeks | Wave 1 UAT sign-off |
| Wave 2 | ~50 (Medium complexity) | 6–8 weeks | Wave 2 UAT sign-off |
| Wave 3 | ~30+ (High complexity) | 8–10 weeks | Wave 3 UAT sign-off |
| Hypercare | All | 2–4 weeks post final wave | Stability confirmed |

9.3 Promotion Process (DEV → QA → PROD)

• Export integration package from DEV

• Import into QA — update externalized parameters for QA

• Run integration tests — obtain sign-off

• Export from QA — import into PROD

• Update externalized parameters for PROD

• Deploy and validate — obtain go-live approval

• Never promote directly from DEV to PROD

10. Testing & Validation

10.1 Testing Levels

| Test Type | Who | Environment | Criteria |
| --- | --- | --- | --- |
| Unit Test | Developer | DEV | Flow deploys, no errors, mapping correct |
| Integration Test | Developer + Ops | QA | End-to-end message flow, system responses correct |
| Performance Test | Architect + Ops | QA/PROD-like | SLA met under expected load |
| UAT | Business Owner | QA/UAT | Business process outcome validated |
| Regression Test | Developer | QA | Existing integrations unaffected |
| Smoke Test | Ops | PROD | Basic connectivity and flow execution post go-live |

10.2 Test Case Template

| Field | Details |
| --- | --- |
| Test Case ID | TC-{INT-ID}-{Sequence} |
| Integration Name |  |
| Test Type | Unit / Integration / UAT |
| Preconditions |  |
| Test Steps |  |
| Input Payload |  |
| Expected Output |  |
| Actual Output |  |
| Pass / Fail |  |
| Tested By |  |
| Date |  |

10.3 Performance Benchmarks

• Document current source platform performance metrics before migration

• Set acceptance criteria: response time, throughput, error rate

• Run load tests simulating peak volume

• Validate against benchmarks before UAT sign-off

10.4 Validation Checklist

• All integration flows deployed and active in target environment

• End-to-end message flow validated for each integration

• Error handling tested (simulate failure scenarios)

• Retry logic validated

• Alerting and monitoring confirmed functional

• Data transformation accuracy validated

• Performance benchmarks met

• Business owner sign-off obtained

11. Cutover & Rollover Considerations

11.1 Cutover Strategy

Option A — Big Bang Cutover

• All integrations switched at once during a single maintenance window

• Higher risk, shorter overall transition period

• Suitable for tightly coupled integration landscapes

Option B — Phased/Wave Cutover (Recommended)

• Integrations switched wave by wave

• Lower risk, longer transition period

• Source platform runs in parallel during transition

11.2 Cutover Plan Template

| Step | Activity | Owner | Duration | Dependency |
| --- | --- | --- | --- | --- |
| 1 | Freeze source platform (no new deployments) | Arch Lead | T-48h |  |
| 2 | Final backup of source artifacts | Developer | T-24h | Step 1 |
| 3 | Final smoke test on target (PROD) | Developer | T-12h | Step 2 |
| 4 | Notify stakeholders of cutover window | PM | T-24h |  |
| 5 | Stop source platform flows | Ops | T=0 | Approved window |
| 6 | Redirect traffic to target platform | Ops/Basis | T=0 | Step 5 |
| 7 | Activate target flows | Developer | T=0 | Step 6 |
| 8 | Smoke test all critical integrations | Developer | T+1h | Step 7 |
| 9 | Business validation | Business Owner | T+2h | Step 8 |
| 10 | Go/No-Go decision | PM + Arch | T+3h | Step 9 |
| 11 | Confirm go-live or initiate rollback | PM | T+3h | Step 10 |

11.3 Rollover Considerations

• Define a hard rollback deadline — the latest point at which rollback is feasible

• Keep source platform flows inactive but not deleted for the duration of hypercare

• Maintain source platform credentials and connections until hypercare is complete

• Document the delta: any messages processed in the target that need to be reconciled if rolling back

• Assign a dedicated rollback decision maker — one person with authority to call it

11.4 Parallel Run Consideration

• For high-criticality integrations, consider running source and target in parallel for a short period

• Compare outputs to validate correctness

• Avoid parallel run for write operations (risk of duplicate records)

12. Rollback Procedures

12.1 Rollback Triggers

Initiate rollback if any of the following occur within the cutover window:

• Critical integration failure that cannot be resolved within the agreed SLA

• Data integrity issues detected (duplicate records, missing data)

• Target platform instability (outage, performance degradation)

• Business process blocked due to integration failure

• Go/No-Go decision is "No-Go" at the defined checkpoint

12.2 Rollback Steps

Step 1: Declare Rollback
   └── PM or Arch Lead declares rollback — notify all stakeholders immediately
Step 2: Stop Target Flows
   └── Undeploy or disable all active flows in target IS tenant
Step 3: Redirect Traffic to Source
   └── Ops/Basis re-routes traffic back to source platform
Step 4: Reactivate Source Flows
   └── Re-enable source platform integrations
Step 5: Validate Source Platform
   └── Smoke test critical integrations on source platform
Step 6: Reconcile In-Flight Messages
   └── Identify and reprocess any messages that were in-flight during cutover
Step 7: Incident Report
   └── Document what went wrong, why rollback was triggered
Step 8: Root Cause Analysis
   └── Identify root cause before scheduling next cutover attempt

12.3 Rollback Decision Matrix

| Scenario | Severity | Rollback? |
| --- | --- | --- |
| 1–2 non-critical flows failing | Low | No — fix forward |
| Critical flow failing, fix ETA < 2h | Medium | No — fix forward with monitoring |
| Critical flow failing, fix ETA > 2h | High | Yes — rollback |
| Data integrity issue detected | Critical | Yes — immediate rollback |
| Platform outage | Critical | Yes — immediate rollback |

13. Go-Live Checklist

All items must be checked and signed off before go-live is declared.

13.1 Technical Readiness

• All integration flows deployed to PROD and in Started status

• All security materials (credentials, certificates) configured in PROD keystore

• All externalized parameters set correctly for PROD

• All destinations in BTP Cockpit tested and passing

• Cloud Connector connected to PROD subaccount and all mappings active

• S/4HANA partner profiles, RFC destinations, and ICF services configured

• Message monitoring accessible and showing no unexpected errors

• Alert rules configured and tested (email/notification on failure)

• Performance test results meet acceptance criteria

• Certificate expiry dates documented (minimum 6 months validity)

13.2 Process & Governance Readiness

• UAT sign-off obtained from all business owners

• Change request approved and documented

• Runbook reviewed and approved by Arch Lead

• Rollback plan reviewed and team is briefed

• Hypercare support roster confirmed (who is on-call)

• Escalation path documented and communicated

• Operations team trained on monitoring and incident handling

• Source platform flows are inactive (not deleted) and available for rollback

13.3 Communication Readiness

• Go-live communication sent to all stakeholders

• Business teams notified of go-live date and time

• Hypercare contact list shared with business

• Post-go-live monitoring schedule confirmed

13.4 Post Go-Live (Hypercare)

• Monitor all flows for first 24 hours intensively

• Daily monitoring summary shared with stakeholders for first 5 days

• All incidents logged and tracked

• Lessons learned session scheduled

• Source platform decommission date confirmed (post hypercare)

14. Things That Can Go Wrong (Risk Register)

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| 1 | Incomplete integration inventory — flows discovered mid-migration | High | High | Conduct thorough discovery; freeze source platform changes early |
| 2 | Undocumented business logic in legacy mappings | High | High | Involve business SMEs in mapping review; allocate buffer time |
| 3 | Certificate expiry during migration | Medium | High | Audit all certs before start; track expiry in a central register |
| 4 | Cloud Connector connectivity issues to on-premise | Medium | High | Test all mappings early; have Basis team on standby |
| 5 | Firewall/network rules blocking BTP traffic | Medium | High | Engage network team early; document all required IP ranges |
| 6 | Credential/secret mismatch between environments | High | Medium | Use externalized parameters; validate each environment separately |
| 7 | Large payload handling failures (> 40MB) | Low | High | Identify large payload flows in assessment; test with actual data volumes |
| 8 | Performance degradation in target vs source | Medium | High | Baseline source performance; run load tests before go-live |
| 9 | Business owner unavailable for UAT sign-off | High | Medium | Identify backup approvers; schedule UAT well in advance |
| 10 | In-flight messages lost during cutover | Medium | High | Define message reconciliation process; use queuing where possible |
| 11 | Duplicate message processing post-cutover | Medium | High | Implement idempotency checks; validate with business |
| 12 | Scope creep — new integrations added mid-project | High | Medium | Enforce change freeze; new requests go to backlog |
| 13 | Timezone/date format issues in transformed data | Medium | Medium | Test with real data; document format expectations explicitly |
| 14 | Role/authorization gaps in target system | Medium | Medium | Conduct access review early; test with actual service accounts |
| 15 | Source platform decommissioned too early | Low | Critical | Do not decommission until hypercare is complete and stable |
| 16 | IDoc partner profile misconfiguration | Medium | High | Validate WE20 settings with Basis; test IDoc flow end-to-end in QA |
| 17 | API throttling or rate limiting on target | Low | Medium | Review API policies; configure retry logic appropriately |
| 18 | Knowledge loss — key team member leaves mid-project | Medium | High | Maintain documentation continuously; cross-train team members |
| 19 | BTP entitlement quota exceeded under load | Low | High | Monitor quota usage; request increases proactively |
| 20 | Rollback not feasible due to data writes in target | Medium | Critical | Avoid parallel writes; define clear rollback deadline |

This runbook is a living document. Update it as the project evolves, decisions are made, and new risks are identified. Version-control all changes and ensure the latest version is accessible to all team members.

Document Control

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | 2026-07-11 | Sookriti | Initial draft |

This framework gives you a solid, production-ready foundation. Here are a few things you can do next:

• Customize the wave plan and RACI to match your actual team structure

• Expand Section 8 with specific adapter configurations relevant to your landscape

• Add an Appendix with system-specific connection details as you gather them

• Convert this into a Word/Confluence document for team distribution

Would you like me to dive deeper into any specific section, add anything else, or generate a visual diagram for any part of this framework?